## Dynamic Timeline
In-Person Convening Dynamic Timeline |  | Convening Date: | 2030-09-30
Step 1: Type the date of your convening in the shaded cell at the top of the sheet. Step 2: As needed, adjust the "Days Before Event" column to change completion dates for activities before or after the event. The columns for "Weeks Before Event" and "Completion Date" are auto-calculated.
Activity | Days Before Event | Weeks Before Event | Completion Date
Identify steering committee members | 84 | 12 | 2030-07-08
Identify potential stakeholders to invite | 84 | 12 | 2030-07-08
Start regular planning meetings with steering committee, including other stakeholders as needed | 84 | 12 | 2030-07-08
Draft event brief/agenda | 56 | 8 | 2030-08-05
Confirm venue | 56 | 8 | 2030-08-05
Confirm date(s) | 56 | 8 | 2030-08-05
Brainstorm potential speakers and how to contact them | 56 | 8 | 2030-08-05
Confirm invitation list | 42 | 6 | 2030-08-19
Consider refreshments | 42 | 6 | 2030-08-19
Send "Save the Date" email | 42 | 6 | 2030-08-19
Begin brainstorming interactive session exercises | 42 | 6 | 2030-08-19
Finalize agenda/speakers | 42 | 6 | 2030-08-19
Develop presentation materials | 42 | 6 | 2030-08-19
Set up webinar platform if needed | 28 | 4 | 2030-09-02
Review session details and plan room set-up | 28 | 4 | 2030-09-02
Circulate invitation (with agenda if able) | 28 | 4 | 2030-09-02
Gather needed on-site materials | 21 | 3 | 2030-09-09
Host pre-convening meeting(s) to ensure speakers, presenters, and planners are familiar with all meeting details and plans | 14 | 2 | 2030-09-16
Send one-week reminder email | 7 | 1 | 2030-09-23
Review RSVPs and consider seating | 7 | 1 | 2030-09-23
Gather refreshments/supplies | 7 | 1 | 2030-09-23
Confirm date & time with speakers | 7 | 1 | 2030-09-23
Request presentation materials from speakers (PowerPoint, etc.) | 7 | 1 | 2030-09-23
Print agendas and handouts | 7 | 1 | 2030-09-23
Ship materials as needed | 7 | 1 | 2030-09-23
Exchange mobile numbers among steering committee | 7 | 1 | 2030-09-23
Send final reminder email | 2 | <1 | 2030-09-28
Host final walk-through meeting to review all event details with steering committee | 2 | <1 | 2030-09-28
Activity | Day of Event |  | Completion Date
Convening |  |  | 2030-09-30
Collect feedback via participant survey |  |  | 2030-09-30
Activity | Days After Event | Weeks After Event | Completion Date
Send thank you email to attendees | 2 | <1 | 2030-10-02
Develop convening readout | 7 | 1 | 2030-10-07
Send thank you notes to presenters and key stakeholders | 7 | 1 | 2030-10-07
Distribute convening readout among steering committee and establish plan for network sustainability | 14 | 2 | 2030-10-14
Formulas:
Completion Date = D34-[Days Before Event]
Completion Date = D34+[Days Before Event]